## Benefits Dashboard
CAREFORWARD GROUP, AI BENEFITS REALISATION FRAMEWORK ¦ Author: Stephanie Onuoha ¦ June 2026 ¦ Version 1.0
Defines measurable expected benefits per AI opportunity · Sets baselines · Tracks outcomes · Reports to governance ¦ github.com/Stephanie-Onuoha/careforward-ai-portfolio
# | AI Opportunity | What We Measure | Baseline (Before AI) | Target (After AI) | How Measured | Frequency | Owner | Expected Annual Value
1 | Voice-to-Text Care Logging | Admin logging time per shift | 35-75 min/shift (5-15 min every hour) Baseline: time audit weeks 1-4 | 7-14 min/shift (1-2 min per hour) 80% reduction target | Monthly time audit: random shift observation, staff self-report survey | Monthly | Home Manager | £18,720-£46,800 per home per year (labour cost saving)
2 | Medication Error Prevention | MAR completion error rate (missed entries, wrong timing, omissions flagged at audit) | Establish baseline in weeks 1-4 via MAR audit before AI launch. Record: errors per 100 administrations | 60-80% reduction in MAR error rate. Target: <2 errors per 100 administrations | Monthly MAR audit by Senior Support Worker. Incident report comparison month-on-month | Monthly | Senior Support Worker / Medication Lead | £10,400+ per year (error-response costs avoided: retraining, supervision overhead, regulatory risk reduction)
3 | Early Health Deterioration Detection | Time from first observed symptom to formal escalation (hours) + 999 call rate per month | Current response time: establish via 3-month incident log review before launch. Record: avg hours, 999 calls/month | 6-12 hours earlier detection vs baseline. 2-3 fewer emergency admissions per month | Quarterly incident log review. Compare: pre-AI vs post-AI escalation time and 999 call frequency | Quarterly | Senior Support Worker / Home Manager | £60,000-£90,000 per year per home (NHS admission cost avoidance: ~£2,500 per emergency admission)
4 | AI-Assisted Handover Summaries | Handover preparation time (minutes per handover) + information gap incidents (missed items reported by incoming shift) | 15-30 min per handover prepared manually. Baseline: staff time survey weeks 1-4 pre-launch | 3-5 min per handover. Zero information gap incidents per month. 80% time reduction | Monthly staff survey (5 questions, 2 mins). Incident log: information gap reports from incoming shift staff | Monthly | Support Worker / Senior Staff | £6,240-£15,600 per home per year (handover time saving + incident reduction)
COMBINED ANNUAL VALUE, ALL 4 OPPORTUNITIES | [7 empty] | £100,000-£160,000 per home per year (labour + clinical impact combined)
GOVERNANCE: Benefits reported monthly to Home Manager. Quarterly summary to ivolve Head of AI. All AI flags human-reviewed. Full audit trail for CQC. Federated architecture: no individual health data transmitted.

## Measurement Templates
MEASUREMENT TEMPLATES, How to Collect Each Metric
TIME AUDIT, Voice-to-Text Logging | Observer watches one full shift per month. Records: start time of each log entry, end time, log type (mood/health/medication/activity). Calculates: total minutes per shift spent on logging. Compares to previous month baseline. Staff also complete 5-question self-report survey.
MAR AUDIT, Medication Error Tracking | Senior staff reviews all MAR sheets monthly. Counts: missed entries, entries without witness signature, entries outside expected time window. Records as errors per 100 administrations. Trend chart updated monthly and shared with Home Manager.
INCIDENT LOG REVIEW, Deterioration Detection | Quarterly review of incident log. For each health deterioration incident: record date/time first symptom observed vs date/time formal escalation made. Calculate average hours between observation and escalation. Count: 999 calls, GP emergency calls, hospital admissions. Compare to same period prior quarter.
STAFF SURVEY, Handover Summary Quality | 5 questions, sent to all staff monthly via WhatsApp or email. Q1: How long did your last handover take? (minutes) Q2: Did the summary cover everything you needed to know? (Yes/Mostly/No) Q3: Were you surprised by anything on shift that should have been in the handover? (Yes/No) Q4: How confident are you in the AI summary accuracy? (1-5) Q5: Any improvement suggestions? (free text)